## Slide 1: College of Information Conference Aug. 1 – 4, 2022
INFO 4306, Group 8 (SADIA MAHBUB)

## Slide 2
Project Scope
Work Breakdown Structure
Project Schedule
Project Budget
Project Checklist
Table of Contents

## Slide 3: Project Scope

## Slide 4: Project Scope
Established in October 2008, the College of Information at the University of North Texas has provided a challenging and nurturing environment for students with nationally recognized and ranked programs at the undergraduate, graduate, and doctoral levels. In alignment with the College of Information’s commitment to quality education and community outreach, the goal of this project is to execute a four-day Career Conference for scholars on the University of North Texas campus.
Project Justification

## Slide 5
The primary stakeholders for this project are the course instructors for INFO 4306/5306, who maintain final authorization of the project. Other clients include the stakeholders of the College of Information, and attendees of the Conference, including scholars and potential undergraduate or graduate students.
Who
What
This document provides the project management plan from contractors to provide a conference, to use across the workforce system. This conference will host 20 guest speakers and approximately 80 attendees in North Texas. This document provides the high-level deliverables for proposal for which a future WBS and finalized budget will be based upon; the anticipated budget of $50,000 will cover costs for staff, equipment, and operating costs.

## Slide 6: ...............................................................
The conference is expected to take place August 1 – 4, 2022. Initiation, Planning, Execution, and Monitoring and Controlling phases are expected to range from final approval and authorization of this scope project through the end of the event. Closing phase is expected to finalize within two weeks after the event.
The conference will take place on the University of North Texas campus, Business Leadership Building. Planning and execution efforts preceding the event will take place online or in-person, at the discretion of the project team.
When
Where

## Slide 7: How
This section describes the high-level deliverables for which the team will be responsible for, as well as risks, constraints, assumptions, and acceptance criteria.
Note: Any activities not defined within the deliverables included within this document will initiate a Change Request and undergo evaluation by the change request board to determine effects on cost, schedule, scope, and client expectations.
High-Level Deliverables

## Slide 8: Location and Parking Arrangements
Contraction of Speakers, Sponsors, and Volunteers
Itinerary and Info Packets
Gratuity Gifts and Swag-Bags
Contraction of Catering, Audio/Video, and Set Up Crew
Health & Safety and Inclimate Weather Plans
Marketing
Promotional Advertisement Video
Website Development
Website Maintenance
Coordination of Post-Conference Meeting
What We Provide

## Slide 9: Work Breakdown Structure

## Slide 11: Project Schedule

## Slide 15: Project Budget

## Slide 17: Project Checklist

## Slide 19: Thank you!